## Sheet1
Detailed list of done work
# | Name of work and materials | Unit | Price in GEL (including VAT) | 2008 year | [7 empty] | 2009 year
|  |  |  | V | VI | VII | VIII | IX | X | XI | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII
1 | Project of architectural and special works |  | 131200 | _______________
2 | Constructive project |  | 37700 |  |  |  |  | X: _________
3 | Temporal buildings,construction of fences and necessary materials(cement,pipes,wood) |  | 9000 |  |  |  |  | XI: _________
4 | Earthwork | 11000 m3 | 44000 |  |  |  |  | 2009 year II: ______
5 | Track works |  | 1000 | bar: 2009 year IV
6 | Layer of the concrete for the foundation |  | 2000
| Concrete B 75 | 81 m3 | 9150 | bar: 2009 year IV
| Wood material | 22 m3 | 6400
| Road metal | 500 m3 | 2500
7 | Knit and concrete of the armature , - 5,6 of the layer of foundation |  | 7000
| Armature A III | 162,37 t | 139283.3
| Armature A I | 3,73 t | 3557.4 |  |  |  |  | 2009 year VI: _______
| Fastening wire | 350 kg | 592.9
| Concrete B 20 | 1698 m3 | 246200
8 | Concrete and knit of the armature on the -5,6 |  | 10000
| Armature A III | 26 t | 31000
| Armature A I | 4 t | 5300
| Fastening wire(of armature) | 500 kg | 1000 | [15 empty] | ______
| Fastening wire (of the gauge) | 600 kg | 3000
| Concrete B20 | 265 m3 | 39750
| Necessary wooden material for the gauge of the diaphragm and columns | 150 m3 | 57000
9 | Necessary wooden material for the gauge for the cover bar at 2,8 | 160 m3 | 60800 | [17 empty] | ___
TOTAL: |  |  | 847433.6